## Sheet1
Project Name | BrowserStack | [8 empty] | Version | -
Processor+A:SB7A:M | [9 empty] | OS | Windows
RAM | - | [8 empty] | Browser | -
Module Name | BrowserStack SEARCH
Reviewed By | Vaishali sonanis | [8 empty] | Date Reviewed on: | 2025-09-01
SR. NO. | TYPE OF TESTING | TEST CASES NO. | TEST CASE NAME | OBJECTIVE | PRE-REQUISITE | STEPS TO BE FOLLOWED | TEST DATA | EXPECTED OUTPUT | ACTUAL OUTPUT | PASSED / FAILED | BUG ID NO. | BUG ROOT CAUSE | WORK ITEM ASSOCIATED | MAJOR / MINOR BUG | IF MAJOR THEN TYPE | TESTED ON | TESTED BY | REMARKS
SEARCH
1 | Functional testing | SC-01 | SC_SearchBar_Visibility | Verify that the search bar is visible on the homepage. | 1. Internet connectivity 2. BrowserStack website link 3. Excel 4. Eclipse Ide 5. Testing Tools 6. Windows 11 OS 7. PC/Laptop 8. Mobile Phone | 1.Open the URL 2.check for search bar | TEST IN PC | Search bar should be visible in home page | Search bar should be visible in home page | PASSED
2 | Functional testing | SC-02 | SC_Search_ProductByExactName | Verify that a product can be searched using its exact name. | 1. Internet connectivity 2. BrowserStack website link 3. Excel 4. Eclipse Ide 5. Testing Tools 6. Windows 11 OS 7. PC/Laptop 8. Mobile Phone | 1.Open the URL 2.check for search bar 3. click on search bar enter any product name | iphone 12 | It display all iphone 12 products | But it showing iphone11 and onepluss mobile phones also | FAILED | SB-01 | IMPLEMENTATION DEFECT
3 | Functional testing | SC-03 | SC_Search_ByBrand | Verify that searching by brand displays products from the same brand. | 1. Internet connectivity 2. BrowserStack website link 3. Excel 4. Eclipse Ide 5. Testing Tools 6. Windows 11 OS 7. PC/Laptop 8. Mobile Phone | 1.Open the URL 2.check for search bar 3.click on search bar enter brand name | Samsung | It display all samsung brand mobiles | But it showing all brands mobiles | FAILED | SB-02 | IMPLEMENTATION DEFECT
4 | Functional testing | SC-04 | SC_Search_WithSpecialCharacters | Verify the system’s behavior when invalid inputs are entered in the search field. | 1. Internet connectivity 2. BrowserStack website link 3. Excel 4. Eclipse Ide 5. Testing Tools 6. Windows 11 OS 7. PC/Laptop 8. Mobile Phone | 1.Open the URL 2.check for search bar 3.click on search bar enter spacial characters | @#$%RTYY | It will display the message like not found | But it showing the products | FAILED | SB-03 | IMPLEMENTATION DEFECT
5 | Functional testing | SC-05 | SC_Search_ExcludeUnrelatedProducts | Verify that only mobile phone products are displayed when searching for mobile phones. | 1. Internet connectivity 2. BrowserStack website link 3. Excel 4. Eclipse Ide 5. Testing Tools 6. Windows 11 OS 7. PC/Laptop 8. Mobile Phone | 1.Open the URL 2.check for search bar 3.click on search bar enter non related product | TV | It will display the message like not found | But it showing the mobile phones products | FAILED | SB-04 | IMPLEMENTATION DEFECT
6 | Functional testing | SC-06 | SC_Search_DisplayRelatedProducts | Verify that all related products are displayed in the search results. | 1. Internet connectivity 2. BrowserStack website link 3. Excel 4. Eclipse Ide 5. Testing Tools 6. Windows 11 OS 7. PC/Laptop 8. Mobile Phone | 1.Open the URL 2.check for search bar 3.click on search bar enter product name | iphone | It will display the all the products | It will display the all the products | PASSED
7 | Functional testing | SC-07 | SC_Search_ProductDescriptionVisibility | Verify that the product description is displayed correctly in the search results. | 1. Internet connectivity 2. BrowserStack website link 3. Excel 4. Eclipse Ide 5. Testing Tools 6. Windows 11 OS 7. PC/Laptop 8. Mobile Phone | 1.Open the URL 2.check for search bar 3.click on search bar enter product | iphone | If i double click one product it will open another tab and display the description about that product | not able to open the another tab it does not show any description | FAILED | SB-05 | IMPLEMENTATION DEFECT
8 | Functional testing | SC-08 | SC_Search_WithNullInput | Verify the behavior of the search functionality when a null (empty) value is entered. | 1. Internet connectivity 2. BrowserStack website link 3. Excel 4. Eclipse Ide 5. Testing Tools 6. Windows 11 OS 7. PC/Laptop 8. Mobile Phone | 1.Open the URL 2.check for search bar 3.click on search bar user not enter anything but click on search button |  | Tell user to enter product in search bar | It will display the all the products in home page only | FAILED | SB-06 | IMPLEMENTATION DEFECT
9 | Functional testing | SC-09 | SC_FILTER_PRODUCT | Verify that the products are coming as per price | 1. Internet connectivity 2. BrowserStack website link 3. Excel 4. Eclipse Ide 5. Testing Tools 6. Windows 11 OS 7. PC/Laptop 8. Mobile Phone | 1.Open the URL 2.check for search bar 3.click on search bar user not enter anything but click on search button | tv under 60 | Should be able to show tv's under 60 | showing tv's without price | FAILED | SB-07 | IMPLEMENTATION DEFECT
10 | Functional testing | SC-10 | SC_RESPONSIVENESS | Check the results of the search page are displayed without error | 1. Internet connectivity 2. BrowserStack website link 3. Excel 4. Eclipse Ide 5. Testing Tools 6. Windows 11 OS 7. PC/Laptop 8. Mobile Phone | 1.Open the URL 2.check for search bar 3.click on search bar user not enter anything but click on search button | tv under 61 | Should be able to show products without errors | Showing products with errors | FAILED | SB-08 | IMPLEMENTATION DEFECT

## Sheet2
Section | Details
Project Name | BrowserStack
Module Name | BrowserStack SEARCH
Release Version | v1.2.3
s | Agile(sprint1)
Prepared By | KARTHIK
Date | 2025-09-01
1. Test Summary
Metric | Count
Total Test Cases | 10
Executed Test Cases | 10
Passed Test Cases | 2
Failed Test Cases | 8
Blocked Test Cases | NA
Not Executed Test Cases | 0
Automation Covered | YES
Manual Test Cases | 10
2. Test Case Status Distribution
Status | Count | Percentage
Passed | 2 | 10%
Failed | 8 | 90%
Blocked | 0 | 0%
Not Executed | 0 | 0%
3. Defect Summary
Metric | Count
Total Defects Logged | 10
Critical Defects | 0
High Severity Defects | 0
Medium Severity Defects | 8
Low Severity Defects | 0
Defects Fixed | 0
Defects Retested & Closed | 0
4. Test Coverage
✅ Requirements Coverage: 9 out of 9 covered.
✅ Code Coverage (if available):0%
✅ Business Scenario Coverage: 100%
5. Observations
ABLE TO IMPROVE PERFORMANCE OF THE SITE SITE IS NOT RESPONDING AS EXPECED AND HAVING UNEXPECTED BEHAVIOUR VALIDATION OF EMAIL IS NOT DONE
6. Risks & Issues
Risk/Issue Description | Impact | Status | Comments
username and password easily available | Medium | Open | hide username and password
after login it will show this "This site can’t provide a secure connection" so this create confusion | Medium | Open | redirect to Home page
7. Recommendations
ABLE TO IMPROVE PERFORMANCE OF THE SITE SITE IS NOT RESPONDING AS EXPECTED